## Risk Register
Meridian Manufacturing (simulated) — Cybersecurity & IT Risk Register
Rolled up from every case in the IT & Cybersecurity portfolio track. Scores are live formulas — edit likelihood, impact, or residual values below and the numbers recalculate.
Risk ID | Title | Category | CSF Function | Source Case | Inh. Likelihood | Inh. Impact | Inherent Score | Res. Likelihood | Res. Impact | Residual Score | Risk Reduction % | Status | Owner | Target Date | Notes
R01 | Log4Shell RCE on the ERP/WMS integration server | Vulnerability | Protect | Vulnerability Assessment (Cyber Case 02) | 4 | 5 |  | 1 | 5 |  |  | Closed | Infrastructure | 2026-01-15 | Patched per refined remediation priority; server also hardened (Cyber Case 03)
R02 | Citrix VPN gateway RCE (refined priority #1 finding) | Vulnerability | Protect | Vulnerability Assessment (Cyber Case 02) | 4 | 5 |  | 1 | 5 |  |  | Closed | Infrastructure | 2026-01-15 | Patched first under the composite-score refined ranking, ahead of naive CVSS-only order
R03 | Legacy TLS 1.0/1.1 still enabled on the EDI integration API | Configuration | Protect | Security Hardening (Cyber Case 03) | 3 | 3 |  | 2 | 3 |  |  | Risk Accepted | Infrastructure | 2026-Q2 | One trading partner's client can't yet negotiate TLS 1.2+; migration scheduled, disclosed and time-boxed
R04 | Vendor support account still active & privileged 8 months post-engagement | Access Control | Identify | Incident Response Tabletop (Cyber Case 04) | 3 | 4 |  | 3 | 4 |  |  | Open | IT Security | 2026-10-01 | Was the actual lateral-movement path used in the tabletop scenario; no compensating control yet
R05 | No ransomware-specific incident response runbook | Response Readiness | Respond | Incident Response Tabletop (Cyber Case 04) | 3 | 4 |  | 3 | 4 |  |  | Open | IT Security | 2026-09-30 | Team improvised containment steps in the tabletop; adapt the VPN outage runbook format
R06 | Phishing reports take ~2 days to reach security (26h detection gap) | Detection Gap | Detect | Incident Response Tabletop (Cyber Case 04) | 4 | 4 |  | 4 | 4 |  |  | Open | IT Security | 2026-10-15 | Single highest-priority recommendation from the tabletop after-action report
R07 | Account-takeover detection rule not yet deployed | Detection Gap | Detect | Log Analysis / Intrusion Detection (prior case) | 3 | 4 |  | 3 | 3 |  |  | In Progress | SOC | 2026-11-01 | Would likely have caught the tabletop's user0147 compromise at hour 0-1 instead of hour 26
R08 | No recurring access review for third-party / vendor accounts | Governance | Govern | Incident Response Tabletop (Cyber Case 04) | 3 | 3 |  | 3 | 3 |  |  | Open | IT Security | 2026-10-01 | Standing process gap, independent of any single incident
R09 | SSH accepted password auth & legacy ciphers (pre-hardening baseline) | Configuration | Protect | Security Hardening (Cyber Case 03) | 3 | 3 |  | 1 | 3 |  |  | Closed | Infrastructure | 2026-01-20 | Access & SSH category went from 0/6 to 6/6 controls passing
R10 | World-writable files & empty-password accounts (pre-hardening baseline) | Configuration | Protect | Security Hardening (Cyber Case 03) | 3 | 3 |  | 1 | 2 |  |  | Closed | Infrastructure | 2026-01-20 | Filesystem & Access categories both reached 100% post-remediation
R11 | Backup recovery point objective is a 4-hour window, unvalidated beyond one incident | Recovery | Recover | Incident Response Tabletop (Cyber Case 04) | 2 | 3 |  | 2 | 2 |  |  | Monitoring | IT Infrastructure | 2026-Q1 review | Restore worked cleanly in the tabletop; RPO tightening is a future efficiency question, not a current gap
R12 | 181 lower-severity scan findings outside the 8-hour remediation window | Vulnerability | Protect | Vulnerability Assessment (Cyber Case 02) | 3 | 2 |  | 3 | 2 |  |  | Open | Infrastructure | 2026-Q4 backlog | Refined plan closed 29.0% of composite risk in the first 8 hours; the remainder is tracked backlog, not ignored
R13 | No policy trigger tying account deprovisioning to HR/vendor contract end dates | Governance | Govern | Synthesized across Cyber Case 04 findings | 3 | 3 |  | 3 | 3 |  |  | Open | IT Security | 2026-10-01 | The policy-level root cause underneath both R04 and R08 — one fix closes both symptoms
R14 | Warehouse & Ops VPN accounts use single-factor authentication | Access Control | Protect | Synthesized across IT Case 01, IT Case 04, Cyber Case 02, Cyber Case 04 | 4 | 4 |  | 4 | 4 |  |  | Open | IT Security | 2026-11-15 | The VPN gateway recurs as an initial-access or availability theme in four separate cases; MFA is the common fix
R15 | KB self-service articles still building toward target adoption | Response Readiness | Respond | Knowledge Base & Runbook Set (IT Case 04) | 2 | 2 |  | 2 | 1 |  |  | Monitoring | IT Support | 2026-Q2 review | 25% adoption assumption modeled in that case; higher adoption further reduces technician load

## GRC Summary
GRC Summary — live rollup of the Risk Register sheet
Every value below is a formula referencing 'Risk Register' — no hand-typed totals.
Total risks tracked
Total inherent risk score
Total residual risk score
Overall risk reduction %
Status breakdown
Closed
Open
In Progress
Risk Accepted
Monitoring
Residual risk by CSF function
Govern
Identify
Protect
Detect
Respond
Recover