PROCESS IMPROVEMENT CHARTER

AP Invoice Approval Cycle Time

| Field | Detail |
| --- | --- |
| Project sponsor | VP Finance |
| Process owner | Accounts Payable Manager |
| Prepared by | Business Analyst — Process Improvement |
| Status | Recommended — pending sponsor sign-off |
| Scope | Accounts Payable invoice approval workflow, all departments |

This is a simulated case study built for a business-analyst portfolio. Brightpath Distribution, its people, and the figures below are illustrative; the discovery method, the analysis, and the workbook behind it are real and reproducible — see cycle_time_analysis.xlsx.

# 1. Executive Summary

Brightpath Distribution's accounts-payable invoice approval process takes an average of 12.8 business days from invoice receipt to payment, against vendor terms that reward payment inside 10 days. A one-month sample of 120 invoices, pulled from AP timestamps and approver email logs, shows the delay is structural, not occasional: every invoice of $500 or more is routed through the same three sequential approvals — department manager, finance manager, and controller — regardless of whether it is a $600 office-supply order or a $60,000 equipment purchase.

The direct cost is measurable: this sample alone forfeited $10,401 in early-payment discounts in one month, an estimated $124,815 annualized. Nothing in the process is unfixable — the fix is to differentiate approval requirements by dollar amount, remove manual data entry for recurring vendors, and replace untracked email routing with a workflow tool that has visibility and backup approvers. Modeled against this same invoice population, that redesign cuts average cycle time to 4.3 days (a 66% reduction) and is projected to net roughly $75,000 in year one and $97,000 in every year after, against a combined tool and implementation cost of $49,600.

# 2. Problem Statement

Finance leadership raised two recurring complaints: vendors increasingly declining to offer early-payment discount terms to Brightpath, citing unreliable payment timing, and AP staff spending a disproportionate amount of time chasing approvals rather than processing invoices. Neither complaint pointed to a specific cause, only a feeling that “invoices take too long.” This charter exists to answer, with data, where the time actually goes and what a fix is worth.

# 3. Current-State Process

See the companion exhibit, process-map.html, for the full swimlane diagram. In summary: every invoice is manually re-keyed from PDF into the accounting system by an AP clerk (avg. 1.3 days), then routed by individual email to a department manager (avg. 4.2 days), a finance manager (avg. 3.6 days), and a controller (avg. 4.2 days) in sequence — for any invoice at or above $500, with no exceptions for size. No backup approver is defined for any of the three roles, so a single approver's absence stalls the invoice until they return. Approval status is not tracked anywhere outside individual inboxes.

# 4. Root-Cause Analysis

Structured as 5 Whys, starting from the symptom finance raised:

| Why | Finding |
| --- | --- |
| 1. Why do invoices take ~13 days to pay? | They pass through 3 sequential manual approvals plus manual data entry before payment is scheduled. |
| 2. Why 3 approvals for every invoice? | The approval policy was never updated after the company's headcount and invoice volume grew; it was written when total monthly invoice volume was roughly a third of today's. |
| 3. Why does each approval take 3–4 days? | Requests are single email threads with no reminders, no visibility, and no deadline. An approver has to notice, open, and act on each one individually. |
| 4. Why is there no reminder or visibility system? | AP has never had a workflow tool; the process was built for a much smaller, lower-volume operation and grew by habit rather than design. |
| 5. Why does data entry take over a day? | Every invoice, including the ~75% from recurring, known vendors with a consistent format, is keyed in by hand rather than captured automatically. |

Root cause: the approval policy and the tooling around it were designed for a smaller company and never revisited as volume grew. The fix is not “work faster” — it is redesigning the policy to match risk to invoice size, and giving approvers a tool that surfaces work instead of burying it in email.

# 5. Future-State Recommendation

Three changes, implemented together:

- Tier approvals by invoice amount: under $500 stays department-manager-only (unchanged); $500–$10,000 drops to department-manager-only; $10,000–$50,000 requires department + finance manager; above $50,000 keeps the full three-approval chain.

- Deploy OCR/auto-capture for the ~75% of invoice volume from established, recurring vendors, eliminating manual re-keying for that population.

- Replace email routing with a lightweight approval workflow tool: automatic reminders, a defined backup approver for each role, and a shared queue so AP can see where any invoice actually sits.

Modeled row-by-row against the same 120-invoice sample (see the Future-State Model and Future-State Projection tabs in cycle_time_analysis.xlsx), this reduces average cycle time from 12.8 to 4.3 days — a 66% reduction — and is projected to recover $124,815/year in early-payment discounts that are currently forfeited.

# 6. Success Metrics

| Metric | Current | Target (Month 6) |
| --- | --- | --- |
| Average invoice cycle time (receipt to payment) | 12.8 days | ≤ 5.0 days |
| % of eligible invoices capturing early-payment discount | 22% | ≥ 80% |
| Invoices routed through all 3 approval tiers | 82% (all $500+ invoices) | ≈ 7% (only Tier 3, >$50K) |
| Invoices with no defined backup approver | 100% | 0% |

# 7. Implementation Plan

| Phase | Timeline | Key activities |
| --- | --- | --- |
| 1. Policy redesign & sign-off | Weeks 1–2 | Finalize tier thresholds with Finance leadership; update the AP approval policy document; identify and confirm backup approvers for each role. |
| 2. Tool selection & configuration | Weeks 3–6 | Select and configure workflow/routing tool and OCR capture tool; integrate with the existing accounting system; build the tiered routing rules. |
| 3. Pilot | Weeks 7–8 | Run the new process for one department's invoices in parallel with the old process; compare cycle times; fix routing-rule edge cases. |
| 4. Company-wide rollout & training | Weeks 9–10 | Roll out to all departments; train approvers and AP staff; publish the updated policy and escalation path. |
| 5. Monitor & adjust | Weeks 11–16 | Track the Section 6 metrics monthly; revisit tier thresholds if volume in any tier looks miscalibrated. |

# 8. Risks & Mitigations

| Risk | Mitigation |
| --- | --- |
| OCR misreads non-standard invoice formats from one-off vendors | Auto-capture is scoped only to the ~75% of volume from recurring, known-format vendors; one-off vendors keep manual entry, flagged as a known limitation rather than forced through OCR. |
| Approvers don't adopt the new tool and keep using email | Old routing is disabled, not left as a parallel option; training in Phase 4 is mandatory and tied to the policy update, not optional. |
| Raising a department manager's authority to single-approve up to $10,000 increases risk exposure | Threshold was set with Finance leadership using Brightpath's existing delegation-of-authority policy, not chosen unilaterally by this project; spot-audits of Tier 1 approvals continue for the first two quarters. |
| Benefit estimate depends on assumptions (queue-time reduction %, OCR adoption) that may not hold exactly | All assumptions are isolated in the Future-State Model tab as labeled, editable cells — the pilot in Phase 3 will validate them against real data before company-wide rollout. |

# 9. Approval

| Role | Name | Signature | Date |
| --- | --- | --- | --- |
| Project Sponsor (VP Finance) |  |  |  |
| Process Owner (AP Manager) |  |  |  |
| Business Analyst |  |  |  |