CHANGE MANAGEMENT PLAN

Colton Regional Supply Warehouse Integration

| Field | Detail |
| --- | --- |
| Project sponsor | COO |
| Change lead | HR Director |
| Prepared by | Business Analyst — Change Management |
| Status | Approved — integration in progress |
| Scope | Warehouse operations integration, 2 Colton sites into Brightpath operations |

This is a simulated case study built for a business-analyst portfolio. Brightpath Distribution, Colton Regional Supply, and the details below are illustrative; the stakeholder analysis and RACI model behind this plan are real and reproducible — see stakeholder_analysis.xlsx.

# 1. Background

Brightpath Distribution acquired Colton Regional Supply, a smaller regional distributor with two warehouse sites and roughly 85 employees, six weeks ago. The two companies' warehouse operations must integrate onto a single WMS, a single shift/scheduling policy, and a single reporting structure within four months, without disrupting order fulfillment for either customer base. The acquisition was announced to Colton employees only at signing; how the integration is run from here will determine whether it reads as a partnership or a takeover.

# 2. Change Impact Assessment

| Change area | Who's affected | Impact | Current readiness |
| --- | --- | --- | --- |
| Warehouse management system (WMS) | Colton warehouse staff & ops managers (Brightpath system replaces Colton's) | High | Low — no exposure to the new system yet |
| Reporting lines | Colton Ops Managers (now report into Brightpath VP Ops) | High | Medium — expected, but structure not yet finalized |
| Shift & scheduling policy | All warehouse staff, both sites | Medium | Medium — some policies already similar |
| Safety & incident-reporting procedures | All warehouse staff, both sites | Medium | High — procedural, less identity-charged |
| Payroll & benefits harmonization | All Colton staff | High | Low — financially sensitive, not yet communicated in detail |
| Colton brand/identity | Colton staff and long-standing Colton customers | Medium (symbolic) | Low — tied directly to job-security anxiety |

# 3. Stakeholder Engagement Approach

Full detail in stakeholder_analysis.xlsx and the accompanying power/interest map. In summary, by quadrant:

- Manage Closely (COO, VP Ops, Colton GM, HR Director) — weekly working sessions; co-own every major decision jointly, not unilaterally from the Brightpath side.

- Keep Informed (both sites' Ops Managers and warehouse staff) — the group carrying the most day-to-day disruption and the least formal power. Two-way channels, not announcements: town halls with open Q&A, and a standing channel for questions that gets answered within 48 hours, tracked and visible.

- Keep Satisfied (CEO, key Colton-region customers) — periodic milestone updates; protect their confidence without pulling them into operational detail they don't need.

- Monitor (IT, Finance/Payroll, general customer base) — kept current through standing project channels; escalate to Manage Closely only if a specific issue in their area surfaces.

The single biggest resistance risk identified in stakeholder interviews was asymmetric treatment: Colton staff explicitly worried about being folded into Brightpath's way of doing things with no input, versus a genuine two-way integration. Every activity in the accompanying RACI matrix mirrors Colton and Brightpath roles at each level deliberately, for this reason.

# 4. Communication Plan

| Phase | Audience | Message | Channel | Frequency | Owner |
| --- | --- | --- | --- | --- | --- |
| 1. Announcement (Wk 1) | All staff, both companies | What's changing, what isn't, and what happens next | All-hands town hall + written FAQ | Once, live | COO + Colton GM (joint) |
| 2. Discovery & listening (Wk 2-3) | Warehouse staff & ops managers, both sites | We want your input on how this actually works day to day | Small-group listening sessions | 2x per site | HR Director + local Ops Managers |
| 3. Design & co-creation (Wk 4-8) | Ops managers, IT, HR | Here's what we heard and how it shaped the design | Working sessions + biweekly written update | Biweekly | VP Ops + Colton GM |
| 4. Pre-go-live (Wk 9-10) | All warehouse staff | What your first day on the new system looks like, concretely | Team briefings + one-page cutover guide | Weekly | Local Ops Managers |
| 5. Go-live (Wk 11) | All warehouse staff | Real-time support during cutover | On-floor support + hotline | Continuous, cutover weekend | IT Lead + Ops Managers |
| 6. Reinforcement (Wk 12-16) | All staff | What's working, what we're still fixing, and how to raise an issue | Biweekly written update | Biweekly | HR Director |

# 5. Training Plan

| Audience | Topic | Format | Timing |
| --- | --- | --- | --- |
| Colton warehouse staff | New WMS — daily-use functions | Hands-on, in small groups, on the actual warehouse floor | Weeks 9-10, before go-live |
| Colton Ops Managers | New WMS — full administrative functions + reporting | Instructor-led, remote or on-site | Weeks 7-8 |
| Brightpath warehouse staff | Any workflow changes from the harmonized shift/scheduling policy | Team briefing | Weeks 9-10 |
| All warehouse staff, both sites | Unified safety & incident-reporting procedure | In-person briefing + posted quick-reference card | Week 9 |

# 6. Resistance Risk Register

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| Colton staff perceive the integration as a takeover, not a partnership | High | High | Joint ownership of every major decision by the Colton GM and Brightpath VP Ops; mirrored roles in the RACI matrix; Colton GM co-delivers the announcement, not just Brightpath leadership. |
| Key Colton warehouse staff leave before cutover, straining fulfillment | Medium | High | Retention conversations with named at-risk individuals (identified by local Ops Managers) before the announcement goes company-wide; competitive-with-Brightpath compensation confirmed early, not left ambiguous through the transition. |
| Brightpath Ops Managers treat their own processes as the default without genuine two-way design | Medium | Medium | Design sessions explicitly structured to start from "what works well at each site today," not "how Brightpath already does it"; HR Director sits in on design sessions specifically to check for this pattern. |
| Training doesn't stick and staff revert to old workarounds after go-live | Medium | Medium | On-floor support continues for two full weeks post-cutover, not just cutover weekend itself; 30-day review (Section 8) explicitly checks adoption, not just system uptime. |

# 7. Adoption Success Metrics

| Metric | Target |
| --- | --- |
| Staff attendance at listening sessions (Phase 2) | ≥ 80% of warehouse staff, both sites |
| Voluntary turnover, Colton sites, during the integration window | No increase over the trailing 12-month baseline rate |
| WMS daily active use rate, both sites, 30 days post-go-live | ≥ 95% of transactions logged in the new system, not the old one or a workaround spreadsheet |
| Unresolved staff questions in the standing Q&A channel, older than 48 hours | Zero, tracked weekly |
| Order fulfillment accuracy, both sites, during cutover week | No degradation versus the trailing 8-week average |

# 8. Approval

| Role | Name | Signature | Date |
| --- | --- | --- | --- |
| Project Sponsor (COO) |  |  |  |
| Change Lead (HR Director) |  |  |  |
| Business Analyst |  |  |  |