## Overview
Case 03 — Stakeholder Analysis
Supports the Change Management Plan for integrating Colton Regional Supply's warehouse operations into Brightpath Distribution after acquisition. Two tabs: a power/interest grid (who to engage, and how) and a RACI matrix for the nine key integration activities.
Color legend
Blue text | Hardcoded input — power/interest rating or RACI assignment
Yellow fill | Key assumption
Black text | Formula

## Power-Interest Grid
Power / Interest Grid
High threshold — a rating above this counts as "high" (1-5 scale) |  |  | 3
Stakeholder | Power (1-5) | Interest (1-5) | Quadrant | Engagement strategy
CEO (Brightpath) | 5 | 2 | Keep Satisfied | Brief at milestones only; do not overload with operational detail — needs confidence the integration is on track, not the mechanics.
COO / Integration Sponsor | 5 | 5 | Manage Closely | Weekly steering check-in; owns final call on any scope or timeline change.
VP Operations (Brightpath) | 4 | 5 | Manage Closely | Co-owns the plan; weekly working session with the integration team.
Colton Regional GM | 4 | 5 | Manage Closely | Co-owns the plan; primary voice for Colton staff concerns — must be seen as a partner, not a subordinate, or the whole rollout reads as a takeover.
Brightpath Warehouse Ops Managers | 3 | 4 | Keep Informed | Involved in shift/scheduling and safety-procedure design; their buy-in determines floor-level adoption.
Colton Warehouse Ops Managers | 3 | 5 | Keep Informed | Same involvement as Brightpath counterparts, deliberately mirrored — asymmetric treatment here is a top resistance risk.
IT / Systems Integration Lead | 3 | 3 | Monitor | Standing biweekly sync; escalation path for data-migration issues.
HR Director | 4 | 4 | Manage Closely | Co-owns communications and the training plan; accountable for consistent messaging.
Finance / Payroll | 3 | 3 | Monitor | Consulted on payroll-system cutover timing only; not involved in operational design.
Brightpath Warehouse Staff | 2 | 4 | Keep Informed | Town halls + team-lead cascade; two-way channel for questions, not one-way announcements.
Colton Warehouse Staff | 2 | 5 | Keep Informed | Highest anxiety group (job security, new management) — most frequent, most concrete communication; specific answers, not general reassurance.
Key Colton-region customers | 3 | 2 | Monitor | Single proactive letter/call ahead of cutover confirming no service disruption; monitor for complaints during go-live week.
Count by quadrant
Manage Closely | 4
Keep Satisfied | 1
Keep Informed | 4
Monitor | 3

## RACI Matrix
RACI Matrix — Integration Activities
R = Responsible · A = Accountable (exactly one per activity) · C = Consulted · I = Informed
Activity | COO / Sponsor | VP Ops (Brightpath) | Colton GM | Warehouse Ops Managers | IT Integration Lead | HR Director | Warehouse Staff | Check
Approve unified WMS platform selection | A | C | C | C | R | I |  | OK
Design unified shift/scheduling policy | I | A | C | R |  | C | I | OK
Communicate role/reporting-line changes to staff | I | C | C | R |  | A | I | OK
Migrate Colton inventory data to unified WMS | I | I | C | R | A |  |  | OK
Deliver cross-training on new WMS & procedures |  | I | I | A | R | C | I | OK
Set unified safety & incident-reporting procedures | I | A | C | R |  | C | I | OK
Finalize integrated org chart & reporting lines | A | C | C | I |  | R | I | OK
Go-live cutover weekend execution | I | A | C | R | C |  | I | OK
Post-integration 30-day review | I | A | C | C | C | C |  | OK
All activities have exactly one Accountable? | Yes — validated