BUSINESS CASE

Automating Inbound Sales-Order Entry

| Field | Detail |
| --- | --- |
| Project sponsor | VP Operations |
| Prepared by | Business Analyst — Business Case & Cost-Benefit |
| Status | Recommended — pending budget approval |
| Decision | Build vs. buy vs. hire: how to handle rising inbound order-entry volume |
| Horizon | 3-year cost-benefit, 8% discount rate |

This is a simulated case study built for a business-analyst portfolio. Brightpath Distribution and the figures below are illustrative; the cost-benefit model, NPV, and payback calculation are real and reproducible — see cost_benefit_analysis.xlsx.

# 1. Executive Summary

Brightpath Distribution's inbound sales-order entry team manually keys customer orders from fax, email PDF, and an EDI portal into the ERP system. Order volume is growing 15% a year, and the team has already grown from 3 to 7 clerks over four years to keep up. The Operations Director has a routine request pending: approve two more hires for next year. This business case exists because that request was never actually evaluated against the alternative — investing in OCR/RPA automation instead.

Modeled over 3 years against the same volume growth: continuing to hire costs $1,592,000. Automating costs $1,512,000 and, combined with fewer downstream order errors, delivers a $210,725 net benefit over hiring — a $165,288 net present value at an 8% discount rate, with a 1.6-year payback. The automation option also avoids adding headcount at all: existing staff absorb the volume through freed-up capacity, redirected to exception handling rather than displaced.

# 2. Problem Statement

Order volume has grown steadily and is projected to keep growing at roughly 15% a year. At current productivity (about 9,500 orders per clerk per year), keeping pace by hiring alone would require the team to grow from 7 to 11 clerks over the next 3 years. Nobody had modeled what that costs against the alternative before this business case — headcount requests were being approved reactively, one hiring cycle at a time.

# 3. Options Considered

| Option | Description | Verdict |
| --- | --- | --- |
| A. Do nothing | Hold headcount at 7 and let the backlog grow as volume outpaces capacity. | Rejected outright — not a serious option. Order-entry delays cascade directly into shipment delays and customer complaints; this was ruled out in the first stakeholder conversation, not modeled financially. |
| B. Hire to keep pace | Add clerks each year at current productivity to match volume growth (7 → 9 → 10 → 11 over 3 years). | Financially modeled — baseline for comparison. |
| C. Invest in OCR/RPA automation | Deploy OCR/RPA to auto-capture and key the fax/email/EDI order formats that follow a consistent template; existing staff handle the remaining manual volume and exceptions. | Financially modeled — recommended. |

# 4. Cost-Benefit Analysis

Full year-by-year build in cost_benefit_analysis.xlsx. Headline comparison over 3 years:

|  | Option B — Hire | Option C — Automate |
| --- | --- | --- |
| Year 1 cost | $484,000 | $584,000 (includes $120,000 one-time implementation) |
| Year 2 cost | $528,000 | $464,000 |
| Year 3 cost | $580,000 | $464,000 |
| 3-year total cost | $1,592,000 | $1,512,000 |
| Headcount, end of Year 3 | 11 clerks | 7 clerks (unchanged) |

The cost comparison alone favors automation by $80,000 over 3 years — a real but modest margin. The fuller picture includes order-entry error costs, which the cost table above doesn't capture: OCR-validated orders have a materially lower error rate (0.6%) than hand-keyed orders (2.5%), and errors are expensive downstream (rework, reshipment, customer-service time, modeled at $35/error). Avoiding those errors on the growing automated share of volume is worth an estimated $130,725 over 3 years on its own — bringing the combined 3-year net benefit of automating to $210,725.

# 5. NPV & Payback

| Metric | Value |
| --- | --- |
| 3-year net benefit (cost avoided + error cost avoided) | $210,725 |
| 3-year NPV @ 8% discount rate | $165,288 |
| Payback period | 1.62 years (≈ 1 year, 7 months) |

Year 1 shows a net cost, not a benefit — the $120,000 one-time implementation charge outweighs Year 1's savings before the automation is fully ramped. This is normal for an automation investment and is stated plainly rather than smoothed into a 3-year average: anyone approving this should expect Year 1 to look worse than the status quo before it turns around in Year 2.

# 6. Risk Register

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| OCR misreads non-standard order formats, especially fax | Medium | Medium | Automation adoption is modeled conservatively (65% of volume in Year 1, ramping to 80% by Year 3), not 100% — the remaining share stays on manual entry by design, not as a fallback surprise. |
| Implementation takes longer than planned, delaying the Year 1 benefit further | Medium | Medium | Phased rollout starting with the highest-volume, most consistent order format (EDI-adjacent email PDFs) before extending to fax, so partial benefit starts accruing before full rollout completes. |
| Freed-up clerk capacity isn't actually redirected to useful work, undermining the no-layoffs rationale | Medium | Low-Medium | Redeployment plan (exception handling, order-quality review, customer follow-up on flagged orders) defined and staffed before go-live, not left to be figured out afterward. |
| Volume growth assumption (15%/year) doesn't hold, changing the economics of both options | Low-Medium | Medium | Both options were modeled off the same growth assumption, so a miss affects the comparison's absolute numbers but not materially which option wins — automation's advantage widens, not narrows, if growth is faster than modeled. |

# 7. Recommendation

Invest in OCR/RPA automation for inbound order entry (Option C). It costs less than continuing to hire, avoids growing headcount for a task that's a strong automation candidate, and meaningfully reduces downstream order-error costs — a benefit the headcount-only comparison misses entirely. The case is not a slam dunk in Year 1 (net cost, due to the one-time implementation charge) and should be presented to the budget owner with that caveat explicit, not glossed over.

# 8. Implementation Roadmap

| Phase | Timeline | Key activities |
| --- | --- | --- |
| 1. Vendor selection & scoping | Weeks 1–4 | Select OCR/RPA platform; scope which order formats qualify for auto-capture in Phase 1 (highest-volume, most consistent first). |
| 2. Build & integrate | Weeks 5–12 | Configure templates, exception-handling workflow, and ERP integration; define the clerk redeployment plan for freed capacity. |
| 3. Pilot | Weeks 13–16 | Run automated capture on the Phase 1 order formats in parallel with manual entry; compare accuracy and throughput before cutting over. |
| 4. Full rollout | Weeks 17–20 | Cut over the Phase 1 formats; begin configuring the next tranche of formats toward the Year 2 and Year 3 adoption targets. |
| 5. Monitor & expand | Ongoing | Track auto-capture rate, error rate, and redeployed-capacity utilization monthly; extend to additional formats toward the 80% Year 3 target. |

# 9. Approval

| Role | Name | Signature | Date |
| --- | --- | --- | --- |
| Project Sponsor (VP Operations) |  |  |  |
| Finance Reviewer |  |  |  |
| Business Analyst |  |  |  |